## Sheet1
Activity | A | B | C | D | E | F | G
Prerequisites |  |  | A | A,B | D | C,E | E
Completion Time | 9 | 5 | 8 | 4 | 5 | 3 | 7

## Sheet2
A | Design Phase | 9
B | Board Meeting | 5
C | Site Dev | 8
D | Foundation | 4
E | Slab | 5
F | Wall | 3
G | Finishing | 7