## PERT CPM Dates
| Early Start | Early Finish | Late Start | Late Finish | Completion Time | Slack | Prerequisites
Survey Preparation (Program and Questionnaire) | 2023-07-01 | 2023-07-02 | 2023-07-01 | 2023-07-02 | 1 | 0
Survey Deployment | 2023-07-02 | 2023-07-16 | 2023-07-02 | 2023-07-16 | 14 | 0 | Survey Preparation (Program and Questionnaire)
TDM Program Development | 2023-07-02 | 2023-07-05 | 2023-07-28 | 2023-07-31 | 3 | 26 | Survey Preparation (Program and Questionnaire)
TDM Forecasting and Program Deployment | 2023-07-05 | 2023-07-07 | 2023-07-31 | 2023-08-02 | 2 | 26 | TDM Program Development
Maps (Chapter 1 and 2) | 2023-07-01 | 2023-07-03 | 2023-07-28 | 2023-07-30 | 2 | 27
Field Survey | 2023-07-16 | 2023-07-30 | 2023-07-16 | 2023-07-30 | 14 | 0 | Survey Deployment
Chapter 3 Analysis (Traffic Profiles) | 2023-07-30 | 2023-08-02 | 2023-07-30 | 2023-08-02 | 3 | 0 | Maps (Chapter 1 and 2),Field Survey
Infacility Data Analysis | 2023-07-16 | 2023-07-18 | 2023-07-31 | 2023-08-02 | 2 | 15 | Survey Deployment
Writing Chapter 1 Project Background | 2023-07-30 | 2023-08-02 | 2023-08-02 | 2023-08-05 | 3 | 3 | Maps (Chapter 1 and 2),Field Survey
Writing Chapter 2 Road Profile | 2023-08-02 | 2023-08-05 | 2023-08-02 | 2023-08-05 | 3 | 0 | Chapter 3 Analysis (Traffic Profiles)
Writing Chapter 3 Traffic Profiles | 2023-07-30 | 2023-08-02 | 2023-08-02 | 2023-08-05 | 3 | 3 | Maps (Chapter 1 and 2),Field Survey
Writing Chapter 4 TDM | 2023-07-16 | 2023-07-19 | 2023-08-02 | 2023-08-05 | 3 | 17 | Survey Deployment,TDM Forecasting and Program Deployment
Writing Chapter 5 Infacility Analysis | 2023-07-18 | 2023-07-21 | 2023-08-02 | 2023-08-05 | 3 | 15 | Infacility Data Analysis
Writing Chapter 6 Conclusions and Recommendations | 2023-08-05 | 2023-08-08 | 2023-08-05 | 2023-08-08 | 3 | 0 | Writing Chapter 1 Project Background,Writing Chapter 2 Road Profile,Writing Chapter 3 Traffic Profiles,Writing Chapter 4 TDM,Writing Chapter 5 Infacility Analysis
Finalization | 2023-08-08 | 2023-08-13 | 2023-08-08 | 2023-08-13 | 5 | 0 | Writing Chapter 6 Conclusions and Recommendations

## PERT CPM Table
| Early Start | Early Finish | Late Start | Late Finish | Completion Time | Slack | Prerequisites
Survey Preparation (Program and Questionnaire) | 0 | 1 | 0 | 1 | 1 | 0
Survey Deployment | 1 | 15 | 1 | 15 | 14 | 0 | Survey Preparation (Program and Questionnaire)
TDM Program Development | 1 | 4 | 27 | 30 | 3 | 26 | Survey Preparation (Program and Questionnaire)
TDM Forecasting and Program Deployment | 4 | 6 | 30 | 32 | 2 | 26 | TDM Program Development
Maps (Chapter 1 and 2) | 0 | 2 | 27 | 29 | 2 | 27
Field Survey | 15 | 29 | 15 | 29 | 14 | 0 | Survey Deployment
Chapter 3 Analysis (Traffic Profiles) | 29 | 32 | 29 | 32 | 3 | 0 | Maps (Chapter 1 and 2),Field Survey
Infacility Data Analysis | 15 | 17 | 30 | 32 | 2 | 15 | Survey Deployment
Writing Chapter 1 Project Background | 29 | 32 | 32 | 35 | 3 | 3 | Maps (Chapter 1 and 2),Field Survey
Writing Chapter 2 Road Profile | 32 | 35 | 32 | 35 | 3 | 0 | Chapter 3 Analysis (Traffic Profiles)
Writing Chapter 3 Traffic Profiles | 29 | 32 | 32 | 35 | 3 | 3 | Maps (Chapter 1 and 2),Field Survey
Writing Chapter 4 TDM | 15 | 18 | 32 | 35 | 3 | 17 | Survey Deployment,TDM Forecasting and Program Deployment
Writing Chapter 5 Infacility Analysis | 17 | 20 | 32 | 35 | 3 | 15 | Infacility Data Analysis
Writing Chapter 6 Conclusions and Recommendations | 35 | 38 | 35 | 38 | 3 | 0 | Writing Chapter 1 Project Background,Writing Chapter 2 Road Profile,Writing Chapter 3 Traffic Profiles,Writing Chapter 4 TDM,Writing Chapter 5 Infacility Analysis
Finalization | 38 | 43 | 38 | 43 | 5 | 0 | Writing Chapter 6 Conclusions and Recommendations

## Prerequisites
Activity | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
Prerequisites |  | A | A | C |  | B | E,F | B | E,F | G | E,F | B,D | H | I,J,K,L,M | N
Completion Time | 1 | 14 | 3 | 2 | 2 | 14 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5

## Labels
Index | Label
A | Survey Preparation (Program and Questionnaire)
B | Survey Deployment
C | TDM Program Development
D | TDM Forecasting and Program Deployment
E | Maps (Chapter 1 and 2)
F | Field Survey
G | Chapter 3 Analysis (Traffic Profiles)
H | Infacility Data Analysis
I | Writing Chapter 1 Project Background
J | Writing Chapter 2 Road Profile
K | Writing Chapter 3 Traffic Profiles
L | Writing Chapter 4 TDM
M | Writing Chapter 5 Infacility Analysis
N | Writing Chapter 6 Conclusions and Recommendations
O | Finalization